## Boat Wash admin panel
Boat Wash Admin Panel
|  | GANTT Chart : Boat Wash Admin Panel Release ID: Augurs Tech: Protected Controlled Copy Project ID:ATPL25032022 <SCI.ID.> / Ver: 01.0 |  |  | Resources | Dev 1
[6 empty] | Project Start Date | 2022-03-25 |  | March | [6 empty] | April | [49 empty] | May | [30 empty] | June
 | time axis 2022-03-25 to 2022-09-18
S# | Requirement ID | Task Description | Milestone | Task Description | Resource | Weekday Duration | Start | End | time axis 2022-03-25 to 2022-09-18
1 | BR001 | Admin Panel Theme setup - Admin dashboard - Admin user management - Content management - Transaction Management - Internal testing & fixes | MS-1 |  | Dev 1 | 10 | 2022-03-25 | 2022-04-05 | bar: 2022-03-28 to 2022-03-29
2 | BR002 | User Management development - User name - Email id - Phone number - Address - Last service date - New service request - Action (Add/edit/delete) - Testing and fixes | MS-2 |  | Dev 1 | 10 | 2022-04-06 | 2022-04-16
3 | BR003 | Content Management development (Sub sections) - Welcome screen content management (Upload/add/delete) - Landing page content management (Upload/add/delete) - Home screen content management (Upload/add/delete) - Product page content management (Upload/add/delete) - List of the wash centres - API creation and integration with frontend features - Testing and fixes | MS-3 |  | Dev 1 | 10 | 2022-04-17 | 2022-04-27
4 | BR004 | Transaction Management development - User name - Email id - Phone number - Payment status(Success/failed/pending) - Upgrade plan for the each wash - API creation and its implementation from the frontend features - Testing and fixes | MS-4 |  | Dev 1 | 10 | 2022-04-28 | 2022-05-08
[7 empty] | 1899-12-31 | 0
0
Holiday
[6 empty] | 2021-01-01 | 2021-01-01
[6 empty] | 2021-01-14 | 2021-01-14