## Boat wash (Android)
Boat Wash App
|  | GANTT Chart : Boat Wash App Release ID: Augurs Tech: Protected Controlled Copy Project ID:ATPL07032022 <SCI.ID.> / Ver: 01.0 |  |  | Resources | Dev 1
[6 empty] | Project Start Date | 2022-03-25 |  | March | [6 empty] | April | [49 empty] | May | [30 empty] | June
 | time axis 2022-03-25 to 2022-09-18
S# | Requirement ID | Task Description | Milestone | Task Description | Resource | Weekday Duration | Start | End | time axis 2022-03-25 to 2022-09-18
1 | BR001 | Design and Development (In XML) > Project set up > Splash Screen > Landing page of the app > Can I wash my boat page > Home screen > Sign up > Login > Product page > Check out page > Confirmation page and Sign off page > Internal testing and fixes | MS-1 |  | Dev 1 | 5 | 2022-03-25 | 2022-03-31 | bar: 2022-03-28 to 2022-03-29
2 | BR002 | Development & Functionality > Landing page development > Sailboat or Power boat button selection > Description of Sailboat and Powerboat screen > Can I wash my boat screen development > Testing and fixes | MS-2 |  | Dev 1 | 5 | 2022-04-01 | 2022-04-07
3 | BR003 | Development & Functionality > Sign up /login button functionality to choose any one of them on the Welcome Screen > Sign up page API creation and its implementation as per the required fields > Login page API creation and its implementations as per the required given fields > Internal testing and fixes | MS-3 |  | Dev 1 | 5 | 2022-04-08 | 2022-04-14
4 | BR004 | Development & Functionality > Home page > Search tab > Filter search based on location > Map view on the home screen to show nearest wash boat centre > List of the wash centre API creation > Internal testing and fixes | MS-4 |  |  | 5 | 2022-04-15 | 2022-04-21 | bar: 2022-04-15 to 2022-04-21
5 | BR005 | Development & Functionality > Product page (choose time of boat wash, number of services, Buy CTA button, price for the particular wash centre , description of the boat wash centre) > Checkout page > Stripe payment gateway > Internal testing and fixes | MS-5 |  | Dev 1 | 10 | 2022-04-22 | 2022-05-05
6 | BR006 | Development & Functionality > QR code generation after the successful payment process > Confirmation message on the screen whether your boat can be washed or not > After the wash of users boat sign off that your boat is washed > Internal testing and fixes | MS-6 |  | Dev 1 | 10 | 2022-05-06 | 2022-05-17
[7 empty] | 1899-12-31 | 0
0
Holiday
[6 empty] | 2021-01-01 | 2021-01-01
[6 empty] | 2021-01-14 | 2021-01-14